## WBS - Updated Product Backlog
Module | Subtask | ID | User Stories / Work Package | Initial Estimation (Story Points) | Sprint # | Total Sprint Points | Sprint 1 Done | Sprint 1 Remaining | Sprint 2 Done | Sprint 2 Remaining | Sprint 3 Done | Sprint 3 Remaining | Sprint 4 Done | Sprint 4 Remaining | Sprint 5 Done | Sprint 5 Remaining
1. Accounts & Verification | Customer Registration & Login | 1.1.1 | Design customer registration form | 4 | 1 | 70 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.2 | Implement account creation and field validation | 7 | 1 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3 | Store credentials securely with password hashing | 5 | 1 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.4 | Implement login, session handling and logout | 6 | 1 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Profile & Access | 1.2.1 | Build customer profile page | 4 | 1 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2.2 | Implement profile update functionality | 5 | 1 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2.3 | Implement forgot-password and password-reset flow | 5 | 1 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2.4 | Apply customer, technician and admin role-based access | 6 | 1 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Technician Registration & Verification | 1.3.1 | Create technician service-category and working-area form | 5 | 1 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3.2 | Add NID and skill-evidence upload | 8 | 1 |  | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3.3 | Build admin approve/reject verification workflow | 6 | 1 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3.4 | Show verification status and verified badge | 4 | 1 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Location-Based Discovery | Location Capture | 2.1.1 | Request browser location permission and capture coordinates | 5 | 1 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1.2 | Add manual location and area input | 5 | 2 | 70 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 2.1.3 | Geocode, normalize and save the selected location | 8 | 2 |  | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Nearby Technician Discovery | 2.2.1 | Query verified technicians by service category and location | 8 | 2 |  | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2.2 | Calculate distance/radius and rank nearby results | 8 | 2 |  | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2.3 | Filter and sort by distance, rating and availability | 7 | 2 |  | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2.4 | Build map/list results with technician profile links | 9 | 2 |  | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reliability & Fallback | 2.3.1 | Handle location-permission and map/API errors | 5 | 2 |  | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3.2 | Implement area/service fallback when map results fail | 6 | 2 |  | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3.3 | Test multiple Dhaka locations, empty states and edge cases | 5 | 2 |  | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3.4 | Limit and handle stored location data safely | 4 | 2 |  | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Service Request, Booking & Tracking | Repair Request Creation | 3.1.1 | Build normal repair-request form | 5 | 2 |  | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 3.1.2 | Add issue-photo attachment | 5 | 3 | 70 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 3.1.3 | Validate service category, issue details and required fields | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | 3.1.4 | Save request and generate a unique request ID | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| Booking & Technician Response | 3.2.1 | Build technician incoming-request queue | 5 | 3 |  | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 3.2.2 | Implement accept/reject response workflow | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | 3.2.3 | Send customer confirmation and request notification | 7 | 3 |  | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
| Status, Emergency & Estimate | 3.3.1 | Implement request status transitions from sent to completed | 7 | 3 |  | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
|  | 3.3.2 | Build customer status timeline and tracking view | 5 | 3 |  | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 3.3.3 | Add controlled emergency/urgent request flag | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | 3.3.4 | Display estimated price/time and booking confirmation | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | 3.3.5 | Notify users about important request-status changes | 6 | 3 |  | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
4. Trust, Safety & Feedback | Ratings & Service History | 4.1.1 | Enable rating only after a completed service | 5 | 3 |  | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  | 4.1.2 | Validate and save 1-5 star rating | 5 | 4 | 70 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 4.1.3 | Submit and display written review | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 4.1.4 | Show customer service history | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
| Complaints & Safety | 4.2.1 | Submit complaint for a completed service | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 4.2.2 | Report a safety concern for admin review | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 4.2.3 | Build admin complaint and safety-review queue | 7 | 4 |  | 0 | 7 | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0
|  | 4.2.4 | Record action, resolution and complaint status | 8 | 4 |  | 0 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0
| Review Moderation & Trust | 4.3.1 | Flag abusive, fake or duplicate review candidates using basic rules | 6 | 4 |  | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0
|  | 4.3.2 | Allow admin to hide or restore inappropriate reviews | 6 | 4 |  | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0
|  | 4.3.3 | Show verified-service indicator on eligible reviews | 4 | 4 |  | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0
|  | 4.3.4 | Run rating, complaint and moderation workflow tests | 4 | 4 |  | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0
5. Admin & Platform Management | Admin Dashboard & Master Data | 5.1.1 | Build admin dashboard summary | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 5.1.2 | Search and view customers, technicians and service requests | 5 | 4 |  | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  | 5.1.3 | Manage service categories | 6 | 5 | 70 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0
|  | 5.1.4 | Manage service coverage areas | 4 | 5 |  | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0
|  | 5.1.5 | Verify, suspend or remove technician accounts | 5 | 5 |  | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0
| Dispute, Monitoring & Integration | 5.2.1 | Implement dispute-resolution workflow | 6 | 5 |  | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0
|  | 5.2.2 | Add important platform-activity and admin audit monitoring | 5 | 5 |  | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0
|  | 5.2.3 | Integrate all five modules with shared navigation and API contracts | 7 | 5 |  | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 7 | 0
|  | 5.2.4 | Run end-to-end integration and smoke tests | 7 | 5 |  | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 7 | 0
| QA, Deployment & Handover | 5.3.1 | Prepare and execute user-acceptance test cases | 7 | 5 |  | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 7 | 0
|  | 5.3.2 | Fix critical defects and run regression tests | 7 | 5 |  | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 7 | 0
|  | 5.3.3 | Verify security, roles and technician-verification controls | 5 | 5 |  | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0
|  | 5.3.4 | Configure demo deployment, domain and SSL | 5 | 5 |  | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 5 | 0
|  | 5.3.5 | Complete final documentation, demonstration and handover | 6 | 5 |  | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0
GRAND TOTAL | GRAND TOTAL | GRAND TOTAL | GRAND TOTAL | 350 |  | 350 | 62 | 288 | 68 | 220 | 80 | 140 | 70 | 70 | 70 | 0

## Sprint wise spent
Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 1 | Sprint 1 | Sprint 1 | Sprint 1 | Sprint 1
Person | Level | Weighted | Allocation | Cost | Jira Hour | Level | Weighted | Allocation | Cost | Jira Hour | Level | Weighted | Allocation | Cost | Jira Hour | Level | Weighted | Allocation | Cost | Jira Hour | Level | Weighted | Allocation | Cost | Jira Hour
Md. Jubayer Hasan | Lead | 2 | 40% | 0.8 | 32 | Lead | 2 | 30% | 0.6 | 24 | Lead | 2 | 30% | 0.6 | 24 | Lead | 2 | 30% | 0.6 | 24 | Lead | 2 | 30% | 0.6 | 24
Fahim Ahmed | Senior | 1.3 | 50% | 0.65 | 40 | Senior | 1.3 | 50% | 0.65 | 40 | Senior | 1.3 | 60% | 0.78 | 48 | Senior | 1.3 | 60% | 0.78 | 48 | Senior | 1.3 | 50% | 0.65 | 40
Sheikh Md Rakibul Hasan | Mid | 1 | 30% | 0.3 | 24 | Mid | 1 | 30% | 0.3 | 24 | Mid | 1 | 30% | 0.3 | 24 | Mid | 1 | 30% | 0.3 | 24 | Mid | 1 | 30% | 0.3 | 24
Pallob Nath | Junior | 0.7 | 40% | 0.28 | 32 | Junior | 0.7 | 30% | 0.21 | 24 | Junior | 0.7 | 30% | 0.21 | 24 | Junior | 0.7 | 20% | 0.14 | 16 | Junior | 0.7 | 20% | 0.14 | 16
K.M. Sakif Muhtasim | Mid | 1 | 20% | 0.2 | 16 | Mid | 1 | 20% | 0.2 | 16 | Mid | 1 | 20% | 0.2 | 16 | Mid | 1 | 30% | 0.3 | 24 | Mid | 1 | 30% | 0.3 | 24
TOTAL | TOTAL | TOTAL | 180% | 2.23 | 144 | TOTAL | TOTAL | 160% | 1.96 | 128 | TOTAL | TOTAL | 170% | 2.09 | 136 | TOTAL | TOTAL | 170% | 2.12 | 136 | TOTAL | TOTAL | 160% | 1.99 | 128
Man-weeks spent | Man-weeks spent | Man-weeks spent | Man-weeks spent | 4.46 |  | Man-weeks spent | Man-weeks spent | Man-weeks spent | 3.92 |  | Man-weeks spent | Man-weeks spent | Man-weeks spent | 4.18 |  | Man-weeks spent | Man-weeks spent | Man-weeks spent | 4.24 |  | Man-weeks spent | Man-weeks spent | Man-weeks spent | 3.98
Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | 22.3 |  | Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | 19.6 |  | Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | 20.9 |  | Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | 21.2 |  | Weighted man-days spent | Weighted man-days spent | Weighted man-days spent | 19.9
Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | 207800 |  | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | 163200 |  | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | 124000 |  | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | 82200 |  | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | Actual labor cost cumulative (BDT) | 39800
Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | 70 |  | Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | 70 |  | Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | 80 |  | Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | 68 |  | Earned Value (Points) | Earned Value (Points) | Earned Value (Points) | 62
Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | 350 | 100% | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | 280 | 80% | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | 210 | 60% | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | 130 | 37.14% | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | Cumulative Earned Value (Points) | 62 | 17.71%
Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | 0 |  | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | 3040 |  | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | 680 |  | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | -5017.1429 |  | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | Labor Cost Variance (BDT) | -2989.7143
Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | 70 |  | Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | 70 |  | Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | 70 |  | Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | 70 |  | Planned Value (Points) | Planned Value (Points) | Planned Value (Points) | 70
Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | 350 |  | Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | 280 |  | Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | 210 |  | Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | 140 |  | Cumulative PV (Points) | Cumulative PV (Points) | Cumulative PV (Points) | 70
Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | 0 |  | Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | 0 |  | Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | 0 |  | Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | -10 |  | Schedule Variance (Points) | Schedule Variance (Points) | Schedule Variance (Points) | -8
Schedule status | Schedule status | Schedule status | Schedule status | On Schedule |  | Schedule status | Schedule status | Schedule status | On Schedule |  | Schedule status | Schedule status | Schedule status | On Schedule |  | Schedule status | Schedule status | Schedule status | Behind Schedule |  | Schedule status | Schedule status | Schedule status | Behind Schedule
Sprint 5 Completed Work | Sprint 5 Completed Work | Sprint 5 Completed Work | Sprint 5 Completed Work | Sprint 5 Completed Work | Sprint 5 Completed Work | Sprint 4 Completed Work | Sprint 4 Completed Work | Sprint 4 Completed Work | Sprint 4 Completed Work | Sprint 4 Completed Work | Sprint 3 Completed Work | Sprint 3 Completed Work | Sprint 3 Completed Work | Sprint 3 Completed Work | Sprint 3 Completed Work | Sprint 2 Completed Work | Sprint 2 Completed Work | Sprint 2 Completed Work | Sprint 2 Completed Work | Sprint 2 Completed Work | Sprint 1 Completed Work | Sprint 1 Completed Work | Sprint 1 Completed Work | Sprint 1 Completed Work | Sprint 1 Completed Work
Work Package | Work Package | Work Package | Work Package | Work Package | Done | Work Package | Work Package | Work Package | Work Package | Done | Work Package | Work Package | Work Package | Work Package | Done | Work Package | Work Package | Work Package | Work Package | Done | Work Package | Work Package | Work Package | Work Package | Done
5.1.3 Manage service categories |  |  |  |  | 6 | 4.1.2 Validate and save 1-5 star rating |  |  |  | 5 | 2.1.2 Add manual location and area input [Carryover] |  |  |  | 5 | 1.3.2 Add NID and skill-evidence upload [Carryover] |  |  |  | 8 | 1.1.1 Design customer registration form |  |  |  | 4
5.1.4 Manage service coverage areas |  |  |  |  | 4 | 4.1.3 Submit and display written review |  |  |  | 5 | 3.1.1 Build normal repair-request form [Carryover] |  |  |  | 5 | 2.1.3 Geocode, normalize and save the selected location |  |  |  | 8 | 1.1.2 Implement account creation and field validation |  |  |  | 7
5.1.5 Verify, suspend or remove technician accounts |  |  |  |  | 5 | 4.1.4 Show customer service history |  |  |  | 5 | 3.1.2 Add issue-photo attachment |  |  |  | 5 | 2.2.1 Query verified technicians by service category and location |  |  |  | 8 | 1.1.3 Store credentials securely with password hashing |  |  |  | 5
5.2.1 Implement dispute-resolution workflow |  |  |  |  | 6 | 4.2.1 Submit complaint for a completed service |  |  |  | 5 | 3.1.3 Validate service category, issue details and required fields |  |  |  | 6 | 2.2.2 Calculate distance/radius and rank nearby results |  |  |  | 8 | 1.1.4 Implement login, session handling and logout |  |  |  | 6
5.2.2 Add important platform-activity and admin audit monitoring |  |  |  |  | 5 | 4.2.2 Report a safety concern for admin review |  |  |  | 5 | 3.1.4 Save request and generate a unique request ID |  |  |  | 6 | 2.2.3 Filter and sort by distance, rating and availability |  |  |  | 7 | 1.2.1 Build customer profile page |  |  |  | 4
5.2.3 Integrate all five modules with shared navigation and API contracts |  |  |  |  | 7 | 4.2.3 Build admin complaint and safety-review queue |  |  |  | 7 | 3.2.1 Build technician incoming-request queue |  |  |  | 5 | 2.2.4 Build map/list results with technician profile links |  |  |  | 9 | 1.2.2 Implement profile update functionality |  |  |  | 5
5.2.4 Run end-to-end integration and smoke tests |  |  |  |  | 7 | 4.2.4 Record action, resolution and complaint status |  |  |  | 8 | 3.2.2 Implement accept/reject response workflow |  |  |  | 6 | 2.3.1 Handle location-permission and map/API errors |  |  |  | 5 | 1.2.3 Implement forgot-password and password-reset flow |  |  |  | 5
5.3.1 Prepare and execute user-acceptance test cases |  |  |  |  | 7 | 4.3.1 Flag abusive, fake or duplicate review candidates using basic rules |  |  |  | 6 | 3.2.3 Send customer confirmation and request notification |  |  |  | 7 | 2.3.2 Implement area/service fallback when map results fail |  |  |  | 6 | 1.2.4 Apply customer, technician and admin role-based access |  |  |  | 6
5.3.2 Fix critical defects and run regression tests |  |  |  |  | 7 | 4.3.2 Allow admin to hide or restore inappropriate reviews |  |  |  | 6 | 3.3.1 Implement request status transitions from sent to completed |  |  |  | 7 | 2.3.3 Test multiple Dhaka locations, empty states and edge cases |  |  |  | 5 | 1.3.1 Create technician service-category and working-area form |  |  |  | 5
5.3.3 Verify security, roles and technician-verification controls |  |  |  |  | 5 | 4.3.3 Show verified-service indicator on eligible reviews |  |  |  | 4 | 3.3.2 Build customer status timeline and tracking view |  |  |  | 5 | 2.3.4 Limit and handle stored location data safely |  |  |  | 4 | 1.3.3 Build admin approve/reject verification workflow |  |  |  | 6
5.3.4 Configure demo deployment, domain and SSL |  |  |  |  | 5 | 4.3.4 Run rating, complaint and moderation workflow tests |  |  |  | 4 | 3.3.3 Add controlled emergency/urgent request flag |  |  |  | 6 | [5 empty] | 1.3.4 Show verification status and verified badge |  |  |  | 4
5.3.5 Complete final documentation, demonstration and handover |  |  |  |  | 6 | 5.1.1 Build admin dashboard summary |  |  |  | 5 | 3.3.4 Display estimated price/time and booking confirmation |  |  |  | 6 | [5 empty] | 2.1.1 Request browser location permission and capture coordinates |  |  |  | 5
[6 empty] | 5.1.2 Search and view customers, technicians and service requests |  |  |  | 5 | 3.3.5 Notify users about important request-status changes |  |  |  | 6
[11 empty] | 4.1.1 Enable rating only after a completed service |  |  |  | 5
Grand Total | Grand Total | Grand Total | Grand Total | Grand Total | 70 | Grand Total | Grand Total | Grand Total | Grand Total | 70 | Grand Total | Grand Total | Grand Total | Grand Total | 80 | Grand Total | Grand Total | Grand Total | Grand Total | 68 | Grand Total | Grand Total | Grand Total | Grand Total | 62

## Pivot
FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints | FixBondhu - Module, Sprint and Cost Summary ¦ 5 Sprints
Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points. | Sprints 1 and 2 are behind schedule; Sprints 3, 4 and 5 are on schedule. Sprint 5 closes all 350 story points.
Labor Cost (BDT) | Labor Cost (BDT) | Direct Cost (BDT) | Direct Cost (BDT) | Contingency (BDT) | Contingency (BDT) | COST BASELINE (BDT) | COST BASELINE (BDT) | COST BASELINE (BDT) | Total Story Points | Total Story Points | Total Story Points
207800 |  | 23000 |  | 20040 |  | 250840 |  |  | 350
Module-wise Estimation | Module-wise Estimation |  | Sprint-wise Delivery and Cost Baseline | Sprint-wise Delivery and Cost Baseline | Sprint-wise Delivery and Cost Baseline | Sprint-wise Delivery and Cost Baseline | Sprint-wise Delivery and Cost Baseline |  | Risk / Opportunity Summary | Risk / Opportunity Summary | Risk / Opportunity Summary
Module | Story Points |  | Sprint | Start | End | Planned Points | Cost Baseline (BDT) |  | Measure | Measure | BDT
1. Accounts & Verification | 65 |  | 1 | 2026-07-27 | 2026-08-09 | 70 | 45090 |  | Threat EMV before response | Threat EMV before response | 43690
2. Location-Based Discovery | 70 |  | 2 | 2026-08-10 | 2026-08-23 | 70 | 55640 |  | Residual threat EMV / contingency | Residual threat EMV / contingency | 20040
3. Service Request, Booking & Tracking | 70 |  | 3 | 2026-08-24 | 2026-09-06 | 70 | 41800 |  | Opportunity EMV before action | Opportunity EMV before action | 22170
4. Trust, Safety & Feedback | 65 |  | 4 | 2026-09-07 | 2026-09-20 | 70 | 40790 |  | Post-action opportunity EMV | Post-action opportunity EMV | 30230
5. Admin & Platform Management | 80 |  | 5 | 2026-09-21 | 2026-10-04 | 70 | 67520
Grand Total | 350 |  | Grand Total | Grand Total | Grand Total | 350 | 250840
Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Schedule and Earned Value Tracking Summary | Reconciliation Checks | Reconciliation Checks | Reconciliation Checks
Sprint | Done Points | Cum. Done | Cum. Planned | SV (Points) | Cum. EV (BDT) | Cum. PV (BDT) | SV (BDT) | Status | Baseline - Labor - Direct - Contingency | Baseline - Labor - Direct - Contingency | 0
1 | 62 | 62 | 70 | -8 | 44434.5143 | 50168 | -5733.4857 | Behind Schedule | Final Remaining Story Points | Final Remaining Story Points | 0
2 | 68 | 130 | 140 | -10 | 93169.1429 | 100336 | -7166.8571 | Behind Schedule | Sprint Baseline Total - Project Baseline | Sprint Baseline Total - Project Baseline | 0
3 | 80 | 210 | 210 | 0 | 150504 | 150504 | 0 | On Schedule | Five-sprint Story Points - Total Story Points | Five-sprint Story Points - Total Story Points | 0
4 | 70 | 280 | 280 | 0 | 200672 | 200672 | 0 | On Schedule | Total Done Points - Total Story Points | Total Done Points - Total Story Points | 0
5 | 70 | 350 | 350 | 0 | 250840 | 250840 | 0 | On Schedule | Final Schedule Variance (Points) | Final Schedule Variance (Points) | 0
[9 empty] | Behind Schedule Count - Required 2 | Behind Schedule Count - Required 2 | 0
[9 empty] | On Schedule Count - Required 3 | On Schedule Count - Required 3 | 0
Formulas:
Contingency (BDT) = [Contingency (BDT)]+Config!$B10-1

## Config
FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints | FixBondhu - Configuration and Cost Assumptions ¦ 5 Sprints
Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets. | Yellow cells are editable planning assumptions. Linked outputs update the WBS, sprint-cost, risk and Pivot sheets.
Project Assumptions | Project Assumptions |  | Level / Weight | Level / Weight |  | Person | Project Role | Level | Weight | Day Rate (BDT)
Project Name | FixBondhu |  | Junior | 0.7 |  | A | Team Lead | Lead | 2 | 4000
Project Start | 2026-07-27 |  | Mid | 1 |  | B | Backend Developer | Senior | 1.3 | 2600
Project Duration (calendar days) | 70 |  | Senior | 1.3 |  | C | Frontend Developer | Mid | 1 | 2000
Project End | 2026-10-04 |  | Lead | 2 |  | D | QA / Tester | Junior | 0.7 | 1400
Sprint Count | 5 |  |  |  |  | E | UI/UX Designer | Mid | 1 | 2000
Sprint Length (calendar days) | 14
Capacity / person / sprint (working days) | 10
Base Mid-level Rate (BDT/day) | 2000
Currency | BDT
Direct Non-Labor Cost Inputs | Direct Non-Labor Cost Inputs | Direct Non-Labor Cost Inputs | Direct Non-Labor Cost Inputs | Direct Non-Labor Cost Inputs |  | Story-Point Estimation Scale Used in the Detailed WBS | Story-Point Estimation Scale Used in the Detailed WBS | Story-Point Estimation Scale Used in the Detailed WBS | Story-Point Estimation Scale Used in the Detailed WBS | Story-Point Estimation Scale Used in the Detailed WBS
ID | Cost Item | Sprint # | Amount (BDT) | Why It Is Needed |  | Points | Meaning | Meaning | Meaning | Meaning
C1 | Cloud development/deployment hosting | 5 | 8000 | Staging and final demonstration hosting allowance. |  | 4 | Simple UI/configuration task | Simple UI/configuration task | Simple UI/configuration task | Simple UI/configuration task
C2 | Map / location API testing | 2 | 6000 | Geocoding and nearby-technician tests across several Dhaka locations. |  | 5 | Small work package with one clear logic path | Small work package with one clear logic path | Small work package with one clear logic path | Small work package with one clear logic path
C3 | Domain and SSL | 5 | 2500 | Public demo endpoint and secure HTTPS setup. |  | 6 | Medium workflow or validation task | Medium workflow or validation task | Medium workflow or validation task | Medium workflow or validation task
C4 | Test devices, connectivity and test data | 5 | 4000 | System/UAT testing under different devices and network conditions. |  | 7 | More complex workflow or integration task | More complex workflow or integration task | More complex workflow or integration task | More complex workflow or integration task
C5 | Documentation, presentation and admin | 5 | 2500 | Final documentation, handover and presentation-related expenses. |  | 8 | High-complexity API, security or data task | High-complexity API, security or data task | High-complexity API, security or data task | High-complexity API, security or data task
TOTAL DIRECT NON-LABOR COST | TOTAL DIRECT NON-LABOR COST | TOTAL DIRECT NON-LABOR COST | 23000 | Must reconcile to the cost baseline summary. |  | 9 | Most complex map/results or cross-component task | Most complex map/results or cross-component task | Most complex map/results or cross-component task | Most complex map/results or cross-component task
Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes | Method and Source Notes
Cost baseline formula | Cost baseline formula | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency. | Labor cost + direct non-labor cost + residual threat EMV contingency.
Labor formula | Labor formula | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights. | Weighted man-days x BDT 2,000; weighted allocation uses the instructor level weights.
Contingency rule | Contingency rule | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved. | Only post-response Threat EMV is added to the baseline. Opportunity savings remain separate until achieved.
Team-role mapping | Team-role mapping | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable. | The five names come from the FixBondhu presentation. Roles and levels remain editable.
Schedule source | Schedule source | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints. | Updated five-sprint plan: 27 Jul 2026 to 04 Oct 2026, 70 calendar days, five two-week sprints.
Instructor reference | Instructor reference | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0. | Instructor sample weights: Junior 0.7, Mid 1.0, Senior 1.3 and Lead 2.0.
Progress scenario | Progress scenario | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule. | Done by sprint: 62, 68, 80, 70, 70. Cumulative SV: -8, -10, 0, 0, 0. Sprints 1-2 are behind; Sprints 3-5 are on schedule.
Formulas:
Project Assumptions = B6+[Project Assumptions, row above]-1
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This scenario deliberately shows exactly two behind-schedule sprints followed by three on-schedule sprints, with all 350 points complete in Sprint 5.

## Risk & Opportunity
FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan | FixBondhu - Project-Specific Threats and Opportunities ¦ 5-Sprint Plan
EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate. | EMV = probability x cost impact/saving. Only residual Threat EMV is added to contingency; opportunity savings remain separate.
Threat EMV Before Response | Threat EMV Before Response | Threat EMV Before Response | Residual Threat EMV / Contingency | Residual Threat EMV / Contingency | Residual Threat EMV / Contingency | Opportunity EMV Before Action | Opportunity EMV Before Action | Opportunity EMV Before Action | Post-Action Opportunity EMV | Post-Action Opportunity EMV | Post-Action Opportunity EMV
43690 |  |  | 20040 |  |  | 22170 |  |  | 30230
ID | Type | Risk / Opportunity Event | Related Phase | Reserve / Target Sprint | Probability | Cost Impact / Saving (BDT) | EMV (BDT) | Strategy | Response Action | Post-Response Probability | Residual / Post-Action EMV (BDT)
T1 | Threat | Map/location API is slower than planned or gives unreliable nearby results. | Module 2: Location Discovery | 2 | 40% | 15800 | 6320 | Mitigate | Run an early API spike, test several Dhaka locations, monitor quota and keep an area/service fallback. | 20% | 3160
T2 | Threat | Account/technician verification or personal-data handling fails security or UAT checks. | Module 1: Accounts & Verification | 1 | 35% | 18600 | 6510 | Mitigate | Store minimum data, hash passwords, apply role-based access and test the verification workflow before sign-off. | 15% | 2790
T3 | Threat | Emergency, price-estimation or complaint features expand beyond the agreed student-project scope. | Module 3: Request & Booking | 2 | 40% | 27200 | 10880 | Avoid / Control | Freeze must-have scope; keep good-to-have items separate and require Team Lead approval for changes. | 15% | 4080
T4 | Threat | Exam or academic workload makes a key member unavailable at a critical point. | Project-wide | 1 | 45% | 10000 | 4500 | Mitigate | Maintain an availability calendar, assign backup reviewers and check the next two weeks at every sprint review. | 25% | 2500
T5 | Threat | Interfaces fail when all five modules are combined during integration and testing. | Integration & Testing | 5 | 40% | 16000 | 6400 | Mitigate | Define shared API/data contracts early and run a smoke test after each module sign-off. | 20% | 3200
T6 | Threat | Fake or duplicate technician profiles pass verification, or admin controls are too weak. | Module 5: Admin | 5 | 30% | 12000 | 3600 | Mitigate | Use a verification checklist, duplicate-field checks, admin audit notes and fake-profile test cases. | 15% | 1800
T7 | Threat | Deployment or an external service fails during the final demonstration or handover. | Deployment & Closure | 5 | 25% | 9200 | 2300 | Mitigate | Prepare a deployment checklist, configuration backup, rollback steps and a recorded/local demo fallback. | 10% | 920
T8 | Threat | Fake, abusive or unfair ratings reduce trust and create complaint-handling gaps. | Module 4: Trust & Feedback | 4 | 30% | 10600 | 3180 | Mitigate | Allow ratings only after completed requests and add basic moderation/reporting before module sign-off. | 15% | 1590
O1 | Opportunity | Student or free-tier cloud credits reduce hosting and deployment expenditure. | Deployment & Closure | 5 | 60% | 8000 | 4800 | Exploit | Check eligibility and quota before deployment and use the free tier if it safely supports the demo. | 80% | 6400
O2 | Opportunity | Reusable authentication, map and form components reduce coding and QA effort. | Modules 1-5 | 2 | 50% | 10600 | 5300 | Exploit | Create a small reusable component set and standardize forms, status, validation and API wrappers. | 70% | 7420
O3 | Opportunity | Early prototype feedback identifies usability problems before formal UAT. | Module 3 + UAT | 4 | 45% | 10600 | 4770 | Enhance | Run a short task-based walkthrough after the booking flow is stable and fix only high-value findings. | 65% | 6890
O4 | Opportunity | Test-case and documentation preparation can run in parallel with development. | Integration & Closure | 5 | 50% | 6800 | 3400 | Enhance | Prepare tests, acceptance criteria and documentation skeletons during development sprints. | 65% | 4420
O5 | Opportunity | A consistent UI pattern across all five modules reduces design and frontend effort. | Modules 1-5 | 1 | 65% | 6000 | 3900 | Exploit | Create a FixBondhu UI pattern set in Module 1 and reuse it unless a later module has a genuine difference. | 85% | 5100